## Sheet1
| Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb
Evaluation of methods and tools expert - Geert
Activity 1: Contribution to the evaluation, prepared by the OECD, of the performance of the Fiscal Discipline Council
Deliverable 1a- Preliminary contribution to the OECD evaluation | Dec: Delivered
Deliverable 1b- Final contribution to the OECD evaluation | bar: Apr; Jul
Activity 2: Scoping, coordination and quality review of the work of two experts providing recommendations to upgrade macroeconomic and fiscal forecasting methods and tools
Deliverables 2a - Terms of reference of the (1) macroeconomic and of the (2) fiscal experts | Dec: Delivered
Deliverable 2b – Review and executive summary – recommendations on macroeconomic forecasts | bar: Apr
Deliverable 2c - Review and executive summary – recommendations on fiscal forecasts | bar: Apr
Activity 3: Coordination and facilitation of a workshop building capacity on the upgraded forecasting methods and tools
Deliverable 3: Workshop | bar: Sep
Activity 4: coordination and quality control of an assessment of 2022 budget forecasts
Deliverable 4 – Review of an assessment of 2022 budget forecasts | bar: Jan
Marco expert - Joao
Activity 1: Assist DG REFORM in the elaboration of the potential output functionality in line with the FDC’s current approach
Deliverable 1: Technical report describing the progress achieved and containing recommendations for the way forward | bar: Apr
Activity 2: Assist DG REFORM in the assessment on how to enhance the FDC’s operational capacity to assess the MoF’s macroeconomic forecasts
Deliverable 2: Report with operational recommendations to further enhance the FDC’s operational forecasting capacity | bar: Jun
Activity 3: Assist DG REFORM in contributing to a workshop on macro-fiscal forecasting and analysis
Deliverable 3: Workshop material and presentations | bar: Sep
Activity 4: Assist DG REFORM in the assessment on the macroeconomic projections of the 2022 budget/stability programme
Deliverable 4: Assessment report on the macro outlook in the budget | bar: Nov
Fiscal expert - Ruben
Activity 1: Assist DG REFORM in the elaboration of an excel-based fiscal forecasting model
Deliverable 1a: A (disaggregated) fiscal forecasting model in excel | bar: Oct
Deliverable 1b: Technical report providing detailed documentation of the fiscal forecasting model | bar: Nov
Activity 2: Assist DG REFORM in contributing to a workshop on macro-fiscal forecasting and analysis (responsible for the fiscal part)
Deliverable 2: Workshop material and presentations | bar: Sep
Activity 3: Assist DG REFORM in the assessment of the 2022 budget/stability programme (fiscal projections and analysis of fiscal policy)
Deliverable 3: Assessment report on the 2022 budget | bar: Oct